## Current Iteration
|  | Iteration Number: |  |  |  | 2
|  | Expected Total effort: |  |  |  | 300
|  | Days In Sprint: |  |  |  | 7
Burndown Chart
User Stories |  | Days (Points Completed) | [19 empty] | Remaining
Product Backlog Items | Beginning Balance | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | Task Balance | Percentage Completed
User Stories #1 - Design the Game Idea (2) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0
User Stories #2 - Design the Main Menu (8) | 0 | Days (Points Completed) 1: 0; Days (Points Completed) 2: 0; Days (Points Completed) 3: 0; Days (Points Completed) 4: 0; Days (Points Completed) 5: 0; Days (Points Completed) 6: 0; Days (Points Completed) 7: 0 | 0
User Stories #3 - Main Characters (64) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0
User Stories #4 - Design the Last Stage (32) | [21 empty] | 0
User Stories #5 - Design the First Stage (32) + (4) | 4 | Days (Points Completed) 1: 2; Days (Points Completed) 2: 0; Days (Points Completed) 3: 0; Days (Points Completed) 4: 1; Days (Points Completed) 8: 0; Days (Points Completed) 9: 0; Days (Points Completed) 10: 0; Days (Points Completed) 11: 0; Days (Points Completed) 12: 0; Days (Points Completed) 13: 0; Days (Points Completed) 14: 0 | 1 | 75%
User Stories #6 - NPCs Enemies (32) | [21 empty] | 0
User Stories #7 - Bosses Enemies (32) | [21 empty] | 0
User Stories #8 - NPCs Friends (16) | [21 empty] | 0
User Stories #9 - Camera Movements (32) | 0 | Days (Points Completed) 1: 0; Days (Points Completed) 2: 0; Days (Points Completed) 3: 0; Days (Points Completed) 4: 0; Days (Points Completed) 5: 0; Days (Points Completed) 6: 0; Days (Points Completed) 7: 0 | 0
User Stories #10 - Design the Loading Screen (4) | 0 | Days (Points Completed) 1: 0; Days (Points Completed) 2: 0; Days (Points Completed) 3: 0; Days (Points Completed) 4: 0; Days (Points Completed) 5: 0; Days (Points Completed) 6: 0; Days (Points Completed) 7: 0 | 0
User Stories #11 - Design an UI system for the game (16) + (4) | 4 | Days (Points Completed) 1: 0; Days (Points Completed) 2: 2; Days (Points Completed) 3: 0; Days (Points Completed) 4: 0; Days (Points Completed) 5: 0; Days (Points Completed) 6: 0; Days (Points Completed) 7: 0 | 2 | 50%
User Stories #12 - Game Manual and Documentation (2) | 0 | Days (Points Completed) 1: 0; Days (Points Completed) 2: 0; Days (Points Completed) 3: 0; Days (Points Completed) 4: 0; Days (Points Completed) 5: 0; Days (Points Completed) 6: 0; Days (Points Completed) 7: 0 | 0
User Stories #13 - Create the Planet Terrain (32) | 32 | [20 empty] | 32 | 0%
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
Effort Remaining | 40 | 38 | 36 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 35 | 12.5%
Ideal Trend | 40 | 34.2857 | 28.5714 | 22.8571 | 17.1429 | 11.4286 | 5.7143 | - | - | - | - | - | - | - | - | - | - | - | - | - | -
Note on G4: For an Accurate Burndown Chart and Ideal Trend, Fill in the expected working days in an Iteration (1 Week = 5 Days). You can additionally choose to hide columns that are not needed. If your Iteration is 2 weeks long, you can hide columns M through V and place 10 in this box. Default Formula Assumes 20 days

## Burndown Chart
d